## ورقة1
Num | Title | Discrebtion | Duration | Importance | depends on | Assigned to | needed data | progress
1 | check modified sequence | check the modification of the way blink sequence is inputed and combine it into the raspberry pi server | three days | important | nothing | mohab | eeg data from device | almost done
2 | get left and right eye movement | test and make a model to detect left and right eye movement | two weeks | important | need data | tarek | eeg data from device | in progress
3 | integrate left & right eye move into main server | put the model into the main server | two days | important | task 2 | tarek & mohab | live eeg data from device
4 | getting gyro and PPG from device | extract these data from Muse2 | two days | important | nothing | mohab | gyro & acc & PPG data from device | done
5 | add features to mobile app | add some features like fall detection, heart rate display, etc… | two weeks | important | task4 | Anas | gyro & acc & PPG data from device | deleted
6 | make desktop application | make desktop app that allow the user to controll almost every thing | two weeks | very important | Task1 | mansour & mohab | no | in progress
7 | make real calibration function | make useable calibration function and integrate it into the server | three days | very important | Task1 | mohab & mansour | eeg data from device | almost done
8 | implement MORSE code into system | add MORSE code into system and make it useable | two days | important | Task1 | mohab | eeg data from device | done
9 | test the system on real subjects | find patients and test the system on them and document the results | one week | very important | all tasks If we can | all team members | no
10 | make the report | make the full report | four weeks | very important | all tasks If we can | all team members | no
11 | make the presentation | make the presentation and rehers well on it | four weeks | very important | all tasks If we can | all team members | no
12 | get the concentration levels | get the level of concentration and relaxation and add it to the system | one week | important | nothing | mansour & mohab | eeg data from device
13 | make the system flixable | make the system able to work without any combonent of the system but the server | three days | important | all tasks If we can | mohab | no | in progress
14 | try to control any app on computer | try to add the ability to control a simple app on the computer (galary) | three days | important | task 6 | mohab & mansour | no
15 | control using gyro and acc |  | three days | important |  |  |  | in progress
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32